## Project_Summary
Project Summary
|  | Planned Dates |  |  |  | Actual Dates
Goal ID | Goal Description | Dev Start | Dev End | Deployment on Test | Deployment on Prod | Dev Start | Dev End | Deployment on Test | Deployment on Prod | Status
1 | Comparing environment Setup for Data Migration | [8 empty] | Completed
2 | Architecture/Component Design | [8 empty] | Completed
3 | Environment Setup | [8 empty] | Analysis done. Waiting for Approval
4 | Financial data Migration | [8 empty] | In progress. Identifying list of tables
5 | McLeod Data Source Migration | [8 empty] | In progress. Identifying list of tables
6 | SmartStream Data Source Migration | [8 empty] | In progress. Identifying list of tables
7 | Gardner Data Source Migration
8 | Data Analytics report creation | [8 empty] | Not yet started

## Project_Plan_Details
S.No | Goal | Task Number | Tasks | Dependency/Prerequest | Owner | Resource | Days | Plan Start Date | Plan End Date | Revise Start Date | Revise End Date | Actual Start Date | Actual/Revised End Date | Status | Remark
1 | Comparing environment Setup for Data Migration
|  | 1.1 | AWS/ Azure/ On Premise Pricing |  | Sudhakar | Rajaram |  |  |  |  | 2019-04-05 |  |  | Completed
|  | 1.2 | Components/Tools evaluation for AWS/Azure |  | Sudhakar | Rajaram |  |  |  |  | 2019-04-05 |  |  | Completed
|  | 1.3 | Provide the pricing details to Stakeholders for review and finalize the environment and budget |  | Sudhakar | Rajaram |  |  |  |  | 2019-04-05 |  |  | Completed
|  | 1.4 | Environment definition
2 | Architecture/Component Design
|  | 2.1 | Component Architecture diagram |  | Sudhakar | [5 empty] | 2019-03-29 |  |  | Completed
|  | 2.2 | Data Flow diagram |  | Sudhakar | [5 empty] | 2019-03-29 |  |  | Completed
|  | 2.3 | Logical Architecture diagram |  | Sudhakar | [5 empty] | 2019-03-29 |  |  | Completed
3 | Environment Setup
|  | 3.1 | Create Environment topology | 1.1
|  | 3.2 | Environment bill of material | 1.1
|  | 3.3 | Environmental provisioning | 1.1
|  | 3.4 | Setup the environment | 1.1
|  | 3.5 | Install required components | 1.1
|  | 3.6 | Create Environment Documentation | 1.1
|  | 3.7 | Setup the Security Provision | 1.1
|  | 3.8 | Define Authentication mechanism | 1.1
|  | 3.9 | Define environment governance owners | 1.1
|  | 3.1 | Testing the environments | 1.1
|  | 3.11 | Document the test results | 1.1
|  | 3.12 | Define release and patch cycle for the environments | 1.1
4 | Financial data Migration
|  | 4.1 | Functional specification document preparation |  | Tyler
|  | 4.2 | Technical design specification document preparation |  | Sudhakar
|  | 4.3 | Identify and allocate resources, responsibilities and ownership |  | Sudhakar/Rajaram
|  | 4.4 | Identify which data is to be migrated ( current and historical volume) |  | Tyler/Sudhakar
|  | 4.5 | Identify data source |  | Tyler/Sudhakar
5 | McLeod Data Source Migration
|  | 5.1 | Analysing the data
|  | 5.2 | Profiling
|  | 5.3 | Document profiling observation and present back to stakeholders
|  | 5.4 | Identify Data Quality rules
|  | 5.5 | Document validate data quality rules and present back to stakeholders
|  | 5.6 | Identify target data system
|  | 5.7 | Identify extraction mechanism
|  | 5.8 | Create Target storage ( Transient zone S3) i.e create s3 bucket
|  | 5.9 | Create Hive tables on RAW zone
|  | 5.10. | Identify transformation process
|  | 5.11 | Identify data validation process (Cleansing)
|  | 5.12 | create metadata tags
|  | 5.13 | Data Mapping
|  | 5.14 | ETL scripts development
|  | 5.15 | Loading the data to Certified zone
|  | 5.16 | Create Hive tables on Cetified zone
Migration Cycle
|  | 5.17 | Upload sample Master data
|  | 5.18 | Unit test verify sample master data
|  | 5.19 | Upload and merge sample incremental load data
|  | 5.20. | Unit test verify merged sample data
|  | 5.21 | Workflow scheduling scripts preparation
|  | 5.22 | Data Archival plan /Script
|  | 5.23 | Unit test verify archived sample data
|  | 5.24 | Data Transfer Security/ Data Access roles security
|  | 5.25 | Develop ETL job for Aggregation (Spark engine)
|  | 5.26 | Unit test ETL job for Aggregation
|  | 5.27 | Load the data to Aggregated zone
|  | 5.28 | Develop Hive tables on Aggregated zone
Testing
|  | 5.29 | Create testing plan
|  | 5.30. | create standard test cases
|  | 5.31 | Integration testing
|  | 5.32 | regression testing
|  | 5.33 | data conversion testing
|  | 5.34 | performance testing
|  | 5.35 | user acceptance testing - signoff
|  | 5.36 | Recovery Plan
|  | 5.37 | Go live plan
|  | 5.38 | Production support plan
6 | SmartStream Data Source Migration
|  | 6.1 | Analysing the data
|  | 6.2 | Profiling
|  | 6.3 | Document profiling observation and present back to stakeholders
|  | 6.4 | Identify Data Quality rules
|  | 6.5 | Document validate data quality rules and present back to stakeholders
|  | 6.6 | Identify target data system
|  | 6.7 | Identify extraction mechanism
|  | 6.8 | Create Target storage ( Transient zone S3) i.e create s3 bucket
|  | 6.9 | Create Hive tables on RAW zone
|  | 6.10.0 | Identify transformation process
|  | 6.11 | Identify data validation process (Cleansing)
|  | 6.12 | create metadata tags
|  | 6.13 | Data Mapping
|  | 6.14 | ETL scripts development
|  | 6.15 | Loading the data to Certified zone
|  | 6.16 | Create Hive tables on Cetified zone
Migration Cycle
|  | 6.17 | Upload sample Master data
|  | 6.18 | Unit test verify sample master data
|  | 6.19 | Upload and merge sample incremental load data
|  | 6.20.0 | Unit test verify merged sample data
|  | 6.21 | Workflow scheduling scripts preparation
|  | 6.22 | Data Archival plan /Script
|  | 6.23 | Unit test verify archived sample data
|  | 6.24 | Data Transfer Security/ Data Access roles security
|  | 6.25 | Develop ETL job for Aggregation (Spark engine)
|  | 6.26 | Unit test ETL job for Aggregation
|  | 6.27 | Load the data to Aggregated zone
|  | 6.28 | Develop Hive tables on Aggregated zone
Testing
|  | 6.29 | Create testing plan
|  | 6.30.0 | create standard test cases
|  | 6.31 | Integration testing
|  | 6.32 | regression testing
|  | 6.33 | data conversion testing
|  | 6.34 | performance testing
|  | 6.35 | user acceptance testing - signoff
|  | 6.36 | Recovery Plan
|  | 6.37 | Go live plan
|  | 6.38 | Production support plan
7 | Gardner Data Source Migration
|  | 7.1 | Analysing the data
|  | 7.2 | Profiling
|  | 7.3 | Document profiling observation and present back to stakeholders
|  | 7.4 | Identify Data Quality rules
|  | 7.5 | Document validate data quality rules and present back to stakeholders
|  | 7.6 | Identify target data system
|  | 7.7 | Identify extraction mechanism
|  | 7.8 | Create Target storage ( Transient zone S3) i.e create s3 bucket
|  | 7.9 | Create Hive tables on RAW zone
|  | 7.10.0 | Identify transformation process
|  | 7.11 | Identify data validation process (Cleansing)
|  | 7.12 | create metadata tags
|  | 7.13 | Data Mapping
|  | 7.14 | ETL scripts development
|  | 7.15 | Loading the data to Certified zone
|  | 7.16 | Create Hive tables on Cetified zone
Migration Cycle
|  | 7.17 | Upload sample Master data
|  | 7.18 | Unit test verify sample master data
|  | 7.19 | Upload and merge sample incremental load data
|  | 7.20.0 | Unit test verify merged sample data
|  | 7.21 | Workflow scheduling scripts preparation
|  | 7.22 | Data Archival plan /Script
|  | 7.23 | Unit test verify archived sample data
|  | 7.24 | Data Transfer Security/ Data Access roles security
|  | 7.25 | Develop ETL job for Aggregation (Spark engine)
|  | 7.26 | Unit test ETL job for Aggregation
|  | 7.27 | Load the data to Aggregated zone
|  | 7.28 | Develop Hive tables on Aggregated zone
Testing
|  | 7.29 | Create testing plan
|  | 7.30.0 | create standard test cases
|  | 7.31 | Integration testing
|  | 7.32 | regression testing
|  | 7.33 | data conversion testing
|  | 7.34 | performance testing
|  | 7.35 | user acceptance testing - signoff
|  | 7.36 | Recovery Plan
|  | 7.37 | Go live plan
|  | 7.38 | Production support plan
8 | Data Analytics Report Creation
Create connection between Aggregated zone to Reporting tool